Project Status Report

Environmental Clearance Services System

(5th Dec, 2022)

Project Status: Green

Progress Summary

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Task | Start Date | End Date | Progress (%) | Remarks |
| Environmental Clearance Services System | 17-Oct-22 | 3-June-23 |  |  |
| Design and Development Phase | 17-Oct-22 | 24-Mar-23 |  |  |
| Requirement Analysis- Software Requirement Specifications(SRS) | 18-Oct-22 | 31-Oct-22 | 100% |  |
| High Level Design Document and Low Level Design | 1-Nov-22 | 25-Dec-22 | 95% |  |
| Development, Testing & Training | 1-Nov-22 | 24-Mar-23 | 15% |  |
| Deployment & Implementation (operational) | 1-Jun-23 | 3-Jun-23 | 0% |  |
| System Support Phase | 4-Jun-23 | 3-Jun-24 |  |  |

Detail Service Wise Progress / Status report (as on 24th October, 2017)

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ECSS | Service | Status SRS (%) | Status HLD (%) | Status Development (%) | Status Deployment (%) | Status Implementation (%) | Current Activity / Status | Remarks |
| Environmental Clearances | ECSS Portal / Content Management System / User Management | 100% | 95% | 90% | 0% | 0% | Development | Design and Development |
| Environmental Clearance for Industry Projects (EA-IEE) | 100% | 95% | 5% | 0% | 0% | Development |
| Environmental Clearance for Energy Projects | 100% | 95% | 0% | 0% | 0% |  |
| Environmental Clearance for Forestry Projects | 100% | 95% | 0% | 0% | 0% |  |
| Environmental Clearance for Road Projects | 100% | 95% | 0% | 0% | 0% |  |
| Environmental Clearance for Transmission Projects | 100% | 95% | 0% | 0% | 0% |  |
| Environmental Clearance for Ground Water Projects | 100% | 95% | 0% | 0% | 0% |  |
| Environmental Clearance for Quarry Projects | 100% | 95% | 0% | 0% | 0% |  |
| Environmental Clearance for Tourism Projects | 100% | 95% | 0% | 0% | 0% |  |
| Environmental Clearance for Others Projects | 100% | 95% | 0% | 0% | 0% |  |

Project Timeline

Project Kick-off

Week 1 to 2

Requirement Analysis

(3 weeks)

We are Here.

Week 4 to 6

System Design/ ECSS portal development

(3 week)

Week 3 to 22

Design, Construct & Implementation

(21 weeks)

Week 23 to 27

UAT/ User Training

(5 week)

Week 28

Operate & Review

GO LIVE

(1 week)

Project Management

Quality Management